## A-6 Job Cost Detail
Mixed Use / Housing / Medical Office Building
| CFMA Construction, Inc. (CFMACI) |  |  | Job Cost Detail Report Summary | [5 empty] | As of:__________
Cost Accounts | Work Descriptions | Original Budget | Approved Change Orders | Total Budgeted Costs | Overruns & Variance | Total Estimated Costs at Completion | Costs To-Date Including Quantity Overruns & Variance | Estimated to Complete | Total Estimated Costs at Completion | Percent Complete
Division 1 - General Conditions
10010 | Supervision | 75000 | 3750 | 78750 | 0 | 78750 | 70000 | 8750 | 78750 | 88.89%
10012 | Mobilization | 16000 | 6000 | 22000 | 3000 | 25000 | 20000 | 5000 | 25000 | 80%
10013 | Insurance & Bonds | 26500 | 0 | 26500 |  | 26500 | 18500 | 7500 | 26000 | 71.15%
10014 | Jobsite support (porta potties, water, utilities, etc.) |  |  |  |  | 0
10015 | Clean Up | 13750 |  | 13750 | 3500 | 17250 | 5000 | 12250 | 17250 | 28.99%
| Sub-Totals | 131250 | 9750 | 141000 | 6500 | 147500 | 113500 | 33500 | 147000
Division 2 - Sitework
20010 | Layout | 7000 | 1500 | 8500 | 650 | 9150 | 8000 | 1150 | 9150 | 87.43%
20012 | Excavation | 50000 | 7500 | 57500 | 5000 | 62500 | 60000 | 2500 | 62500 | 96%
| Sub-Totals | 57000 | 9000 | 66000 | 5650 | 71650 | 68000 | 3650 | 71650
Division 3 - Concrete
30010 | Sub / Landscaping | 65000 |  | 65000 |  | 65000 |  | 65000 | 65000 | 0%
30012 | Footings | 54000 | 5000 | 59000 | 7500 | 66500 | 60000 | 6500 | 66500 | 90.23%
30014 | Short Walls 4' | 15000 | 1500 | 16500 | 10000 | 26500 | 25000 | 1500 | 26500 | 94.34%
30015 | Concrete Slabs | 50000 | 3500 | 53500 |  | 53500 | 53500 | 0 | 53500 | 100%
| Sub-Totals | 184000 | 10000 | 194000 | 17500 | 211500 | 138500 | 73000 | 211500
Division 4 - Masonry
4000 | Masonry | 37500 | 1500 | 39000 | 5000 | 44000 | 35000 | 9000 | 44000 | 79.55%
| Sub-Totals | 37500 | 1500 | 39000 | 5000 | 44000 | 35000 | 9000 | 44000
Division 5 - Metals
5100 | Misc Metals | 12500 | 7500 | 20000 | 10000 | 30000 | 25000 | 5000 | 30000 | 83.33%
| Sub-Totals | 12500 | 7500 | 20000 | 10000 | 30000 | 25000 | 5000 | 30000
Division 6 - Lumber
6100 | Rough Framing | 60000 |  | 60000 | 12500 | 72500 | 58500 | 14000 | 72500 | 80.69%
6400 | Custom Casework | 45500 |  | 45500 | 7500 | 53000 | 25000 | 28000 | 53000 | 47.17%
6700 | Rough Hardware | 1500 | 2500 | 4000 | 5000 | 9000 | 5000 | 4000 | 9000 | 55.56%
| Sub-Totals | 107000 | 2500 | 109500 | 25000 | 134500 | 88500 | 46000 | 134500
Division 7 - Roofing
7200 | Insulation | 45000 |  | 45000 | 4500 | 49500 | 35000 | 14500 | 49500 | 70.71%
7500 | Green Roof | 67500 | 5000 | 72500 | 15000 | 87500 | 35000 | 52500 | 87500 | 40%
7600 | Flashing & Sheetmetal | 15000 | 7500 | 22500 | 11250 | 33750 | 20000 | 13750 | 33750 | 59.26%
| Sub-Totals | 127500 | 12500 | 140000 | 30750 | 170750 | 90000 | 80750 | 170750
Division 8 - Doors/Windows
9000 | Subcontract | 75000 | 1250 | 76250 | 8000 | 84250 | 30000 | 54250 | 84250 | 35.61%
| Sub-Totals | 75000 | 1250 | 76250 | 8000 | 84250 | 30000 | 54250 | 84250
Division 9 - Finishes
9250 | Gypsum Board | 25000 | 2750 | 27750 | 12500 | 40250 | 40000 | 250 | 40250 | 99.38%
9600 | Floor Coverings | 35000 | 5000 | 40000 | 25000 | 65000 | 50000 | 15000 | 65000 | 76.92%
9900 | Painting | 30000 | 3250 | 33250 | 7500 | 40750 | 35000 | 5750 | 40750 | 85.89%
| Sub-Totals | 90000 | 11000 | 101000 | 45000 | 146000 | 125000 | 21000 | 146000
Divison 10 - Specialties
10800 | Clean Room / Lab | 63000 | 7500 | 70500 | 25000 | 95500 | 40000 | 55500 | 95500 | 41.88%
| Sub-Totals | 63000 | 7500 | 70500 | 25000 | 95500 | 40000 | 55500 | 95500
Division 11 - Equipment
11100 | Allowance for Appliances | 67500 | 5000 | 72500 |  | 72500 | 50000 | 22500 | 72500 | 68.97%
| Sub-Totals | 67500 | 5000 | 72500 | 0 | 72500 | 50000 | 22500 | 72500
Division 15 - Mechanical
15400 | Subcontract | 52750 | 5000 | 57750 | 15000 | 72750 | 50000 | 22250 | 72250
| Sub-Totals | 52750 | 5000 | 57750 | 15000 | 72750 | 50000 | 22250 | 72250 | 0
Divison 16 - Electrical
16000 | Subcontract | 45000 | 12500 | 57500 | 11600 | 69100 | 46500 | 23600 | 70100 | 66.33%
| Sub-Totals | 45000 | 12500 | 57500 | 11600 | 69100 | 46500 | 23600 | 70100
| JOB BUDGET & COST TOTALS | 1050000 | 95000 | 1145000 | 205000 | 1350000 | 900000 | 450000 | 1350000 | 66.67%
|  | Original Budget | Approved Change Orders | Total Budgeted Costs | Quantity Overruns & Variance | Total Estimated Costs At Completion | Costs To-Date | Estimated to Complete | Total Estimated Costs at Completion | Percent Complete
| Percent Complete and Earned Revenue Calculations | [5 empty] | Quantity O/R | Variance
| Total Contract Value | 1275000 | 100000 | 1375000 |  |  | 125000 |  | 1500000
-90000
| MARKUP (G&A and Profit) | 225000 | 5000 | 230000 |  |  | 10000 | -90000 | 150000
| Profit as a percent of Contract | 17.65% | 5% | 16.73% |  |  |  |  | 10%
| Earned Revenue | Cost to date / Total Estimated Costs X Total Contract | [6 empty] | 1000000
| Billed To-Date | [7 empty] | 1250000
| Overbilled | [7 empty] | 250000